## PROJECT PLAN1
PROJECT TITLE
AUTOMATED ATTENDANCE TRACKING SYSTEM
TEAM NAME
TEAM JAK OF ALL TRADES
| START DATE | END DATE | REMAINING DAYS |  | TASK COMPLETED | TASK REMAINING | TOTAL TASK
| 2025-02-27 | 2025-05-02 | 17 days |  | 9 | 17 | 26
[7 empty] | Task Start Dates |  | Task End Dates
Phase | Task No. | Task Name | Description | Assigned Person/Team | Estimated Days | Days Used | Plan Start Date | Actual Date Started | Plan End Date | Actual End Date | Status
1. Planning | 1.1 | Client Meeting | Initial meeting with the client to discuss the system project. | TEAM JAK | 1 | 1 | 2025-02-27 | 2025-02-27 | 2025-02-27 | 2025-02-27 | Complete
| 1.2 | Conduct Client Interview | Interview the client to gather insights on requirements and expectations. | TEAM JAK | 1 | 1 | 2025-03-04 | 2025-03-04 | 2025-03-04 | 2025-03-04 | Complete
| 1.3 | Gather Requirements | Collect all necessary system requirements for presentation. | Allen Lagangga | 13 | 12 | 2025-03-05 | 2025-03-05 | 2025-03-17 | 2025-03-16 | Complete
| 1.4 | Client Approval of Requirements Presentation | Present requirements to the client for validation and approval. | TEAM JAK | 1 | 1 | 2025-03-18 | 2025-03-18 | 2025-03-18 | 2025-03-18 | Complete
| 1.5 | High-Level Conceptual Model | Create an overview of the system structure. | Jessa Diano | 9 | 7 | 2025-03-19 | 2025-03-19 | 2025-03-27 | 2025-03-25 | Complete
| 1.6 | Use Case Diagrams | Develop diagrams illustrating system functionalities and user interactions. | Kent Luardo | 9 | 6 | 2025-03-19 | 2025-03-20 | 2025-03-27 | 2025-03-25 | Complete
| 1.7 | Traceability Matrix | Ensure all requirements are mapped to use cases diagram of the system. | Allen Lagangga | 9 | 1 | 2025-03-19 | 2025-03-25 | 2025-03-27 | 2025-03-25 | Complete
| 1.8 | Project Plan | Outline the project timeline, phases, and key milestones | Allen Lagangga | 9 | 3 | 2025-03-19 | 2025-03-23 | 2025-03-27 | 2025-03-25 | Complete
| 1.9 | Set Up Git Project Folder | Establish a repository for version control and collaboration. | Allen Lagangga | 2 | 1 | 2025-03-19 | 2025-03-20 | 2025-03-20 | 2025-03-20 | Complete
2. Design | 2.1 | UI/UX Design in Figma | Create interface prototypes and user flows using Figma for visualization | TEAM JAK | 10 | N/A | 2025-03-27 |  | 2025-04-05 |  | Not Started
| 2.2 | Class Diagram | Define the system’s object-oriented structure, including classes, attributes, and relationships. | Allen Lagangga | 7 | N/A | 2025-03-28 |  | 2025-04-03 |  | Not Started
3. Development | 3.1 | Set Up Backend Framework | Establish the backend infrastructure, configure the server environment, set up a secure and scalable database, and implement RESTful API endpoint. | Allen Lagangga | 8 | N/A | 2025-04-03 |  | 2025-04-10 |  | Not Started
| 3.2 | Implement User Authentication (RBAC & MFA | Ensure secure access control by implementing role-based authentication, multi-factor authentication, and encrypted user credentials. | Jessa Diano | 4 | N/A | 2025-04-07 |  | 2025-04-10 |  | Not Started
| 3.3 | API Documentation | Document RESTful API endpoints, request and response formats, authentication methods, and integration guidelines for developers. | Kent Luardo | 3 | N/A | 2025-04-08 |  | 2025-04-10 |  | Not Started
| 3.4 | Develop Frontend Interfaces | Design and implement responsive user interfaces for admins, instructors, and students, ensuring smooth navigation and accessibility across devices. | TEAM JAK | 17 | N/A | 2025-04-09 |  | 2025-04-25 |  | Not Started
| 3.5 | Develop Registration Module | Enable administrators to register students and instructors, manage user credentials, and update account details in a structured and secure manner | Kent Luardo | 17 | N/A | 2025-04-09 |  | 2025-04-25 |  | Not Started
| 3.6 | Develop Course Enrollment and Assign Module | Allow administrators to assign instructors to courses, enroll students, and manage course schedules efficiently | Allen Lagangga | 17 | N/A | 2025-04-09 |  | 2025-04-25 |  | Not Started
| 3.7 | Develop Instructor Attendance Monitoring | Provide instructors with a real-time attendance tracking interface that utilizes barcode scanning for accurate and automated student check-ins. | Jessa Diano | 17 | N/A | 2025-04-09 |  | 2025-04-25 |  | Not Started
| 3.8 | Develop Lost Device Management Module | Enable administrators to track, unregister instructor devices to prevent unauthorized access | Kent Luardo | 19 | N/A | 2025-04-09 |  | 2025-04-27 |  | Not Started
| 3.9 | Develop Reporting Module | Create attendance reports. | Jessa Diano | 17 | N/A | 2025-04-09 |  | 2025-04-25 |  | Not Started
| 3.10 | Develop Student Portal | Students’ portal to view attendance History and their personal information | Kent Luardo | 17 | N/A | 2025-04-09 |  | 2025-04-25 |  | Not Started
4. Testing | 4.1 | User Acceptance Testing (UAT) | Conduct testing with users to ensure system functionality | TEAM JAK | 5 | N/A | 2025-04-26 |  | 2025-04-30 |  | Not Started
| 4.2 | System Testing | Perform complete system tests for functionality and performance. | TEAM JAK | 5 | N/A | 2025-04-26 |  | 2025-04-30 |  | Not Started
| 4.3 | Security & Performance Testing | Validate security measures and system efficiency. | TEAM JAK | 5 | N/A | 2025-04-26 |  | 2025-04-30 |  | Not Started
5. Deployment | 5.1 | Initial System Review | Review the system for final validation before deployment. | TEAM JAK | 1 | N/A | 2025-04-30 |  | 2025-04-30 |  | Not Started
| 5.2 | Full Deployment Presentation | Officially launch the system and present it to the client. | TEAM JAK | 1 | N/A | 2025-05-02 |  | 2025-05-02 |  | Not Started
Formulas:
TASK REMAINING = IF(AND(ISBLANK([Actual Date Started]), ISBLANK([Actual End Date])), "N/A", IF(ISBLANK([Actual End Date]), TODAY() - [Actual Date Started] + 1, [Actual End Date] - [Actual Date Started] + 1))